## Tasks for Inaugural KOM Series
Time Line between 7 March 2009 & end June 2010
Tasks for Inaugural KOM Series - "Day by Day" to 1 June 2010
Type | Date | Day | Task
Stakeholder-Fed Labor | 2009-03-08 | Sun | Event Organiser posts Business Plan and Information Memorandum to NSW Health & NSW Enviroment and Climate Change
Stakeholder-Fed Labor | 2009-03-21 | Sat | Event Organiser presents to proposed Public Equity Holders
Stakeholder-Fed Labor | 2009-03-22 | Sun | Public Equity Holders notify Event Organiser they agree to progress discussions with I.M.
Stakeholder-Fed Labor | 2009-03-23 | Mon | Event Team and Fed Labor discuss strategy to elicit support from all Stakeholders listed in I.M.
| 2009-03-24 | Tue | 2nd meeting with Fed Labor with other members of Event Team
Stakeholder-Fed Labor | 2009-03-27 | Fri | Event Team and Fed Labor agree strategy to elicit support from all Stakeholders listed in I.M.
Stakeholder-Fed Labor | 2009-03-29 | Sun | Fed Labor executes Term Sheet with Event Team for Inaugural KOM Series in Sydney in April/May 2008
Stakeholder b-blue | 2009-03-22 | Sun | Fed Labor/ET approach Wheelchair Sports Assoc NSW to endorse KOM Challenge Series
Stakeholder b-blue | 2009-03-23 | Mon | Fed Labor and Event Team meet with Wheelchair Sports Assoc NSW re endorsing KOM Challenge Series
Stakeholder b-blue | 2009-03-29 | Sun | Fed Labor and Event Team execute Memo of Understanding with Wheelchair Sports Assoc NSW
Access to Climbs | 2009-03-16 | Mon | Event Team requests consent from Police and Local Council to use 3 KOM Climbs for Individual Time Trials over 6 consecutive w'ends from 1 August '07
Access to Climbs | 2009-03-20 | Fri | Event Team obtains "consent in principal" from Police and Local Council to use 3 KOM Climbs for Individual Time Trials over 6 consecutive w'ends from 1 August '07
Access to Climbs | 2009-04-07 | Tue | ET Team obtains final written approval from Police and Local Council to use 3 KOM Climbs for Individual Time Trials over 6 consecutive w'ends from 1 Aug '07
Stakeholder-APC | 2009-03-29 | Sun | Fed Labor, Event Team and Wheelchair NSW approach Australian Paralympic Committee to co-ordinate involvement of elite Disabled Australian athletes
Stakeholder-APC | 2009-03-31 | Tue | Fed Labor, Event Team and Wheelchair NSW meet with Australian Paralympic Committee to discuss administering involvement of elite Disabled Australian athletes
Stakeholder-APC | 2009-04-05 | Sun | APC commence approaching elite Disabled athletes to compete in KOM Series
Stakeholder-APC | 2009-04-18 | Sat | Fed Labor and Event Team obtain confirmation with Australian Paralympic Committee co-ordinate involvement of elite Disabled Australian athletes
Stakeholder-APC | 2009-05-03 | Sun | APC provides to RTV Producer a short list of 50 elite Disabled athletes to compete in KOM Series
Equipment | 2009-03-10 | Tue | Event Team begins testing electronic Climb Time measurement equipment between AMBit ChipX Decoder, Tissot and Swiss Timing
Equipment | 2009-03-20 | Fri | Event Team selects Climb Time measurement equipment between AMBit, Tissot and Swiss Timing to be purchased by Event Organiser
Equipment | 2009-03-24 | Tue | Test software to publish performance reports to www.KOMpm.com
Stakeholders-Govt | 2009-03-28 | Sat | Fed Labor and Event Organiser conjointly write to Federal Department of Health and Aging seeking its support for KOM Series
Stakeholders-Govt | 2009-03-29 | Sun | Fed Labor and Event Organiser meet with Federal Department of Health and Aging seeking its support for KOM Series
Stakeholders-Govt | 2009-04-04 | Sat | Fed Labor and Event Organiser obtain confirmation from Federal Dept of Health & Aging to support KOM Series
Stakeholders-Govt | 2009-03-23 | Mon | Fed Labor and Event Organiser conjointly write to NSW State Health seeking its support for KOM Series
Stakeholders-Govt | 2009-03-27 | Fri | Fed Labor and Event Organiser meet with NSW State Health seeking its support for KOM Series
Stakeholders-Govt | 2009-04-04 | Sat | Fed Labor and Event Organiser obtain confirmation from NSW State Health to support KOM Series
www.KOMpm.com | 2009-03-23 | Mon | KOM Series Invitation published on www.KOMpm.com with provision for Competitor personal profiles
www.KOMpm.com | 2009-04-26 | Sun | Provide TV RTV Producer shortlist of 20 Abled and 20 Disabled Competitor Profiles
RTV | 2009-03-21 | Sat | Fed Labor and Event Organiser to approach 4 Free to Air and Cable Television Networks re Reality Television episodes
RTV | 2009-03-30 | Mon | Fed Labor and Event Organiser to meet with Television Networks re Reality Television episodes
RTV | 2009-04-25 | Sat | APC provides to RTV Producer a short list of 50 elite Disabled athletes to compete in KOM Series
RTV | 2009-04-26 | Sun | Provide TV RTV Producer shortlist of 20 Abled and 20 Disabled Competitor Profiles
RTV | 2009-05-04 | Mon | Fed Labor, Event Organiser and APC lock-in a Television Network to produce 4 episodes of Reality Television
Stakeholders-Cycling Organisations | 2009-03-06 | Fri | Event Organiser drafts a letter, and postal addresses, for Selected Charity to write to Aust Sports Commission, leading bicycle organisations ie Aust Bicycle Council, Cycling NSW, Cycling Australia, BFA, BNSW seeking them to encourage their members to support KOM Series which will attract new members to cycling and assist disable enhance their QOL
Stakeholders-Cycling Organisations | 2009-03-16 | Mon | Selected Charity writes to Aust Sports Commission, leading bicycle organisations ie Aust Bicycle Council, Cycling NSW, Cycling Australia, BFA, BNSW notifying its prima facie support for KOM Series
Stakeholders-Cycling Organisations | 2009-03-22 | Sun | Fed Labor and Event Organiser conjointly write to Cycling NSW, Cycling Australia, BFA, BNSW referring to Selected Charity's recent letter, and seeking them to encourage their members to support KOM Series which will attract new members to cycling and assist Disable enhance their QOL, and directing all enquiries to the Event Team (Phil/Karen)
Stakeholder-Bike Shops | 2009-03-13 | Fri | Event Organiser drafts a letter and prepares a merge document for Fed Labor and Event Organiser to write to 80 local bicycle shops seeking their support of KOM Series which will attract new members to cycling and assist disable enhance their QOL, with all enquiries to Phil/Karen
Stakeholder-Bike Shops | 2009-03-20 | Fri | Fed Labor and Event Organiser write to 80 local bicycle shops within 10km of a KOM Climb, seeking their support KOM Series which will attract new members to cycling and assist disable enhance their QOL, with all phone and e-mail enquiries to Phil/Karen
Stakeholder-Bike Shops | 2009-03-21 | Sat | Event Team (Phil & Karen) commence receiving phone calls and e-mails from bicycle shops expressing interest in supporting KOM Series
Stakeholder-BUGs & Bicycle Racing Clubs | 2009-03-01 | Sun | Event Organiser drafts a letter and prepares a merge document for Fed Labor and Event Organiser to write to 40 Bicycle Racing Clubs and 20 Bicycle User Groups within 50km of a KOM Climb seeking their support for KOM Series which will attract new members to cycling and assist Disabled enhance their QOL, with all enquiries to Phil/Karen
Stakeholder-BUGs & Bicycle Racing Clubs | 2009-03-29 | Sun | Fed Labor and Event Organiser write to 50 Bicycle Racing Clubs and 30 Bicycle User Groups within 50km of a KOM Climb, seeking their support KOM Series which will attract new members to cycling and assist disable enhance their QOL, with all phone and e-mail enquiries to Phil/Karen
Stakeholder-Charities | 2009-02-28 | Sat | Event Organiser drafts a letter for Wheelchair Sports Assoc to write to 30 Registered Charities notifying its support for KOM Challenge Series
Stakeholder-Charities | 2009-03-10 | Tue | Event Organiser provides a merge document for Wheelchair Sports Assoc to write to 30 Registered Charities
Stakeholder-Charities | 2009-03-14 | Sat | Wheelchair Sports Assoc writes to 30 Registered Charities notifying its support for KOM Series
Stakeholder-Charities | 2009-03-16 | Mon | Fed Labor and Event Organiser conjointly write to 30 Registered Charities, referring to Selected Charity's letter, and asks for the charity's support for KOM Series
Stakeholder-Charities | 2009-03-22 | Sun | Event Team (Phil & Karen) commence phoning and e-mailing 30 charities seeking charity to contact Karen/Phil if interested in KOM Series
CEOs of Top 100 Companies, Partner of Law and Accounting Firms, Heads of Gov. Depts | 2009-02-28 | Sat | EO drafts letter and prepares merge for Wheelchair Sports Assoc to write to Top 100 CEOs, Senior Partner of Law and Accounting Practices, and Heads of Govt Depts inviting their employees to consider KOM Series for both Abled and Disabled employees within their company
CEOs of Top 100 Companies, Partner of Law and Accounting Firms, Heads of Gov. Depts | 2009-03-13 | Fri | Wheelchair Sports Assoc writes to Top 100 CEOs, Senior Partner of Law and Accounting Practices, and Heads of Govt Depts inviting their employees, both Abled and Disabled, to consider KOM Series for both Abled and Disabled employees within their company
CEOs of Top 100 Companies, Partner of Law and Accounting Firms, Heads of Gov. Depts | 2009-03-15 | Sun | Event Team (Phil & Karen) commence receiving phone calls and e-mails from employees from Top 200 companies expressing interest in KOM Series
Stakeholder-Local Councils | 2009-03-02 | Mon | EO drafts letter. prepares a merge for Fed Labor and EO to write to 20 Local Councils within 50km of a KOM Climb seeking support KOM Series which will attract new members to cycling and assist Disabled enhance their QOL, with all enquiries to Phil/Karen
Stakeholder-Local Councils | 2009-03-30 | Mon | Fed Labor and EO write to 20 Local Councils within 50km of a KOM Climb, seeking support KOM Series which will attract new members to cycling and assist disable enhance their QOL, with all phone and e-mail enquiries to Phil/Karen
Stakeholder-Bicycle Suppliers and Tour Operators | 2009-03-08 | Sun | EO drafts letter, prepares a merge for Fed Labor and EO to write to 20 Bicycle Suppliers and 3 Tour Company within 50km of a KOM Climb seeking support KOM Series, with all enquiries to Phil/Karen
Stakeholder-Bicycle Suppliers and Tour Operators | 2009-03-31 | Tue | Fed Labor and EO write to 20 Bicycle Suppliers and 3 Tour Company within 50km of a KOM Climb seeking support KOM Series, with all phone and e-mail enquiries to Phil/Karen
Stakeholder-Cycling Forums | 2009-04-03 | Fri | Event Team e-mails Cycling Forums on the Internet seeking support for KOM Series which will attract new members to cycling and assist disable enhance their QOL
Bicycle Jerseys | 2009-04-26 | Sun | Agree style and supplier of: 29 Fed Labor polka dot KOM Winner jerseys 29 Fed Labor KOM Winner medallions 500Fed Labor King of the Mountain Challenge Series Competitors jerseys
KOM Website | 2009-04-27 | Mon | Publishing individual Climber Profile Pages and Climber Photo on www.KOMpm.com for each of 400 Climbers in Semi-Finals and 100 Climbers in Disabled Finals.
KOM Website | 2009-05-02 | Sat | List Fed Labor Australia as Sole Sponsor, and display logos on “King of the Mountain Performance Measurement” website from 1 April 2007 to end-Nov 2007
KOM Series | 2009-11-12 | Thu | 1st Semi-Final
| 2009-11-17 | Tue | ANZAC Day weekend - no competition
KOM Series | 2009-11-26 | Thu | 2nd Semi-Final
KOM Series | 2009-12-03 | Thu | 3rd Semi-Final
KOM Series | 2009-12-10 | Thu | 4th Semi-Final
KOM Series | 2009-12-16 | Wed | Disabled Final
KOM Series | 2009-12-17 | Thu | 5th Semi-Final and Extras
KOM Series | 2009-12-23 | Wed | Saturday Final
KOM Series | 2009-12-24 | Thu | Sunday Final

## 10 months Time Line
Tasks for Inaugural KOM Series - "Day by Day" to 1 June 2010 | [21 empty] | Tasks for Inaugural KOM Series - "Day by Day" to 1 June 2010 | [24 empty] | Tasks for Inaugural KOM Series - "Day by Day" to 1 June 2010 | [6 empty] | 8 month Time Line from 1 April 2007 to end- November 2007 | [22 empty] | Tasks for Inaugural KOM Series - "Day by Day" to 1 June 2010 | [30 empty] | Tasks for Inaugural KOM Series - "Day by Day" to 1 June 2010 | [30 empty] | Tasks for Inaugural KOM Series - "Day by Day" to 1 June 2010 | [26 empty] | Tasks for Inaugural KOM Series - "Day by Day" to 1 June 2010 | [25 empty] | KOM Series Start Date | [17 empty] | Tasks for Inaugural KOM Series - "Day by Day" to 1 June 2010 | [16 empty] | KOM Series Finish Date
 | time axis 2009-02-22 to 2009-12-25
| Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
1st Semi-Final
2. Remove #N/A's | 2009-02-28: Event Organiser drafts a letter for Wheelchair Sports Assoc to write to 30 Registered Charities notifying its support for KOM Challenge Series; 2009-03-01: Event Organiser drafts a letter and prepares a merge document for Fed Labor and Event Organiser to write to 40 Bicycle Racing Clubs and 20 Bicycle User Groups within 50km of a KOM Climb seeking their support for KOM Series which will attract new members to cycling and assist Disabled enhance their QOL, with all enquiries to Phil/Karen; 2009-03-02: EO drafts letter. prepares a merge for Fed Labor and EO to write to 20 Local Councils within 50km of a KOM Climb seeking support KOM Series which will attract new members to cycling and assist Disabled enhance their QOL, with all enquiries to Phil/Karen; 2009-03-06: Event Organiser drafts a letter, and postal addresses, for Selected Charity to write to Aust Sports Commission, leading bicycle organisations ie Aust Bicycle Council, Cycling NSW, Cycling Australia, BFA, BNSW seeking them to encourage their members to support KOM Series which will attract new members to cycling and assist disable enhance their QOL; 2009-03-08: Event Organiser posts Business Plan and Information Memorandum to NSW Health & NSW Enviroment and Climate Change; 2009-03-10: Event Team begins testing electronic Climb Time measurement equipment between AMBit ChipX Decoder, Tissot and Swiss Timing; 2009-03-13: Event Organiser drafts a letter and prepares a merge document for Fed Labor and Event Organiser to write to 80 local bicycle shops seeking their support of KOM Series which will attract new members to cycling and assist disable enhance their QOL, with all enquiries to Phil/Karen; 2009-03-14: Wheelchair Sports Assoc writes to 30 Registered Charities notifying its support for KOM Series; 2009-03-15: Event Team (Phil & Karen) commence receiving phone calls and e-mails from employees from Top 200 companies expressing interest in KOM Series; 2009-03-16: Event Team requests consent from Police and Local Council to use 3 KOM Climbs for Individual Time Trials over 6 consecutive w'ends from 1 August '07; 2009-03-20: Event Team obtains "consent in principal" from Police and Local Council to use 3 KOM Climbs for Individual Time Trials over 6 consecutive w'ends from 1 August '07; 2009-03-21: Event Organiser presents to proposed Public Equity Holders; 2009-03-22: Public Equity Holders notify Event Organiser they agree to progress discussions with I.M.; 2009-03-23: Event Team and Fed Labor discuss strategy to elicit support from all Stakeholders listed in I.M.; 2009-03-24: 2nd meeting with Fed Labor with other members of Event Team; 2009-03-27: Event Team and Fed Labor agree strategy to elicit support from all Stakeholders listed in I.M.; 2009-03-28: Fed Labor and Event Organiser conjointly write to Federal Department of Health and Aging seeking its support for KOM Series; 2009-03-29: Fed Labor executes Term Sheet with Event Team for Inaugural KOM Series in Sydney in April/May 2008; 2009-03-30: Fed Labor and Event Organiser to meet with Television Networks re Reality Television episodes; 2009-03-31: Fed Labor, Event Team and Wheelchair NSW meet with Australian Paralympic Committee to discuss administering involvement of elite Disabled Australian athletes; 2009-04-03: Event Team e-mails Cycling Forums on the Internet seeking support for KOM Series which will attract new members to cycling and assist disable enhance their QOL; 2009-04-04: Fed Labor and Event Organiser obtain confirmation from Federal Dept of Health & Aging to support KOM Series; 2009-04-05: APC commence approaching elite Disabled athletes to compete in KOM Series; 2009-04-07: ET Team obtains final written approval from Police and Local Council to use 3 KOM Climbs for Individual Time Trials over 6 consecutive w'ends from 1 Aug '07; 2009-04-18: Fed Labor and Event Team obtain confirmation with Australian Paralympic Committee co-ordinate involvement of elite Disabled Australian athletes; 2009-04-25: APC provides to RTV Producer a short list of 50 elite Disabled athletes to compete in KOM Series; 2009-04-26: Provide TV RTV Producer shortlist of 20 Abled and 20 Disabled Competitor Profiles; 2009-04-27: Publishing individual Climber Profile Pages and Climber Photo on www.KOMpm.com for each of 400 Climbers in Semi-Finals and 100 Climbers in Disabled Finals.; 2009-05-02: List Fed Labor Australia as Sole Sponsor, and display logos on “King of the Mountain Performance Measurement” website from 1 April 2007 to end-Nov 2007; 2009-05-03: APC provides to RTV Producer a short list of 50 elite Disabled athletes to compete in KOM Series; 2009-05-04: Fed Labor, Event Organiser and APC lock-in a Television Network to produce 4 episodes of Reality Television; 2009-11-12: 1st Semi-Final; 2009-11-17: ANZAC Day weekend - no competition; 2009-11-26: 2nd Semi-Final; 2009-12-03: 3rd Semi-Final; 2009-12-10: 4th Semi-Final; 2009-12-16: Disabled Final; 2009-12-17: 5th Semi-Final and Extras; 2009-12-23: Saturday Final; 2009-12-24: Sunday Final